# Clinical Migration Effort Estimation

# Executive Summary

This document outlines the estimated effort required for the clinical migration project. The total estimated effort is 480 hours, which translates to approximately 3.0 months of development work based on 8-hour working days and 20 working days per month.

| Metric | Value |
| --- | --- |
| Total Effort | 480 hours |
| Duration (8 hours/day) | 60.0 working days |
| Timeline (20 days/month) | 3.0 months |

# Detailed Component Breakdown

## Login - 4 hours

Complete UI implementation

## SideNav - 8 hours

Complete UI implementation

## Dashboard - 38 hours

Dashboard module with filters, data grids, and score cards

Key Components:

Global Filters Setup (Module-wise) - 12 hours
   6 hrs UI + 6 hrs Backend (factory setup, JPA filters, config-based filter management)

Data Grid Full Setup - 16 hours
   8 hrs Frontend + 8 hrs Backend (columns in RDS)

Score Cards - 10 hours
   5 hrs UI charts + 5 hrs Backend (filter query changes)

## Load Tracker - 22 hours

Load tracking with filters and data grid

Key Components:

Filters - 6 hours
   Backend effort - query optimization for all filters

Data Grid - 16 hours
   UI, actions, backend column config, expanded data, polling

## ID-Based Loader Tracker - 226 hours

Comprehensive loader tracking system with multiple sub-modules

Key Components:

Tabs - 2 hours
   Straightforward tab implementation

Load Tracker Sub-module - 30 hours
   Stepper (10 hrs) + Data Grid (20 hrs - backend columns + UI)

File Tracker - 14 hours
   Mini Sidebar (4 hrs) + Stepper & DataGrid (10 hrs)

Mapping - 20 hours
   DataGrid (8 hrs - UI + Backend) + Popup DataGrid (12 hrs - actions, backend config)

Datasets - 48 hours
   Tabs & Filters (14 hrs) + Query Builder (10 hrs) + Tab DataGrids (24 hrs)

Reports - 96 hours
   Filters (16 hrs) + Score Cards (8 hrs) + DataGrids (24 hrs) + Popup Query Builder (24 hrs) + Additional UI/Backend (24 hrs)

Config - 36 hours
   2 Tabs + DataGrids (18 hrs) + View Page DataGrids (18 hrs)

Related Files - 4 hours
   Standard DataGrid implementation

## Global Config - 182 hours

Global configuration modules with multiple data grids and validations

Key Components:

ICM DataGrid - 52 hours
   DataGrid (12 hrs) + Actions (8 hrs) + Popup DataGrids (20 hrs) + Business Rules/Checks (12 hrs)

UCM DataGrids - 52 hours
   DataGrid (12 hrs) + Actions (8 hrs) + Popup DataGrids (20 hrs) + Business Rules/Checks (12 hrs)

Data Quality - 42 hours
   Filters, multi-step forms/popups, DataGrids and forms

Data Sources - 36 hours
   DataGrid (12 hrs) + Business Rules (12 hrs) + Grid Filters & Column Management (12 hrs)

# Effort Distribution by Component

| Component | Hours | Percentage |
| --- | --- | --- |
| Login | 4 | 0.8% |
| SideNav | 8 | 1.7% |
| Dashboard | 38 | 7.9% |
| Load Tracker | 22 | 4.6% |
| ID-Based Loader Tracker | 226 | 47.1% |
| Global Config | 182 | 37.9% |
| TOTAL | 480 | 100% |

# Key Areas of Effort

The following areas represent the most significant effort in the migration:

1. ID-Based Loader Tracker (226 hours - 47.1%)
   Comprehensive loader tracking system with multiple sub-modules

2. Global Config (182 hours - 37.9%)
   Global configuration modules with multiple data grids and validations

3. Dashboard (38 hours - 7.9%)
   Dashboard module with filters, data grids, and score cards

# Assumptions and Notes

8 working hours per day

20 working days per month

Estimates include both frontend (UI) and backend development effort

Estimates include implementation, unit testing, and code review time

Complex components like DataGrids include column configuration, actions, and backend integration

Query Builder implementations include both UI and backend rule engine setup

Configuration changes for filter management aim to reduce future maintenance effort