## Migration Estimates
Clinical Migration Effort Estimation
PROJECT SUMMARY
Total Effort | 480 hours
Duration (8 hrs/day) | 60.0 working days
Timeline (20 days/month) | 3.0 months
DETAILED BREAKDOWN
Module/Component | Hours | Frontend/Backend Split | Details
Login | 4 |  | Complete UI implementation
SideNav | 8 |  | Complete UI implementation
Dashboard | 38 |  | Dashboard module with filters, data grids, and score cards
• Global Filters Setup (Module-wise) | 12 | UI + Backend | 6 hrs UI + 6 hrs Backend (factory setup, JPA filters, config-based filter management)
• Data Grid Full Setup | 16 | UI + Backend | 8 hrs Frontend + 8 hrs Backend (columns in RDS)
• Score Cards | 10 | UI + Backend | 5 hrs UI charts + 5 hrs Backend (filter query changes)
Load Tracker | 22 |  | Load tracking with filters and data grid
• Filters | 6 |  | Backend effort - query optimization for all filters
• Data Grid | 16 | UI + Backend | UI, actions, backend column config, expanded data, polling
ID-Based Loader Tracker | 226 |  | Comprehensive loader tracking system with multiple sub-modules
• Tabs | 2 |  | Straightforward tab implementation
• Load Tracker Sub-module | 30 | UI + Backend | Stepper (10 hrs) + Data Grid (20 hrs - backend columns + UI)
• File Tracker | 14 |  | Mini Sidebar (4 hrs) + Stepper & DataGrid (10 hrs)
• Mapping | 20 | UI + Backend | DataGrid (8 hrs - UI + Backend) + Popup DataGrid (12 hrs - actions, backend config)
• Datasets | 48 |  | Tabs & Filters (14 hrs) + Query Builder (10 hrs) + Tab DataGrids (24 hrs)
• Reports | 96 | UI + Backend | Filters (16 hrs) + Score Cards (8 hrs) + DataGrids (24 hrs) + Popup Query Builder (24 hrs) + Additional UI/Backend (24 hrs)
• Config | 36 |  | 2 Tabs + DataGrids (18 hrs) + View Page DataGrids (18 hrs)
• Related Files | 4 |  | Standard DataGrid implementation
Global Config | 182 |  | Global configuration modules with multiple data grids and validations
• ICM DataGrid | 52 |  | DataGrid (12 hrs) + Actions (8 hrs) + Popup DataGrids (20 hrs) + Business Rules/Checks (12 hrs)
• UCM DataGrids | 52 |  | DataGrid (12 hrs) + Actions (8 hrs) + Popup DataGrids (20 hrs) + Business Rules/Checks (12 hrs)
• Data Quality | 42 |  | Filters, multi-step forms/popups, DataGrids and forms
• Data Sources | 36 |  | DataGrid (12 hrs) + Business Rules (12 hrs) + Grid Filters & Column Management (12 hrs)
TOTAL EFFORT | 480 |  | 60.0 days ¦ 3.0 months @ 8 hrs/day