## Summary
Metric | Value | Notes
Total effort (hours) | 480 | Planned as 60 working days at 8h/day
Working days | 60 | Equivalent to three 20-day months
Delivery window | 3 calendar months | Assumes parallel UI + backend pairing
Daily staffing | 1 full-time squad | Blend of UI engineer + backend engineer

## Workstream Totals
Workstream | EffortHours
ID-based Loader Tracker | 226
Global Config | 182
Dashboard | 38
Load Tracker | 22
Foundational Shell | 12

## Detailed Tasks
Workstream | Component | Task | EffortHours | PrimaryFocus
Dashboard | Data Grid | End-to-end dashboard data grid setup | 16 | Column definitions in RDS plus frontend grid interactions
Dashboard | Global Filters | Module-aware global filter framework | 12 | Split effort across UI configuration and backend factory methods
Dashboard | Score Cards | KPI score cards with updated queries | 10 | Backend filter queries + chart refresh on the client
Foundational Shell | Login | Login experience refresh | 4 | Full UI revamp, validation, theming consistency
Foundational Shell | Side Navigation | Side navigation redesign | 8 | UI restructuring, navigation states, accessibility pass
Global Config | Data Quality | Multi-step filters/forms | 42 | Filter wizard, popups, supporting data grids
Global Config | Data Sources | Data source grids & rules | 36 | Grid setup, validation rules, filter/reset controls
Global Config | ICM Data Grid | ICM grid + actions + rule checks | 52 | Datagrid, action popups, validations, rules engine tie-ins
Global Config | UCM Data Grid | UCM grid + actions + rule checks | 52 | Mirror of ICM scope for UCM datasets
ID-based Loader Tracker | Config | Tabbed config grids | 18 | Two tabs worth of UI + backend column definitions
ID-based Loader Tracker | Config | Detail view grids | 18 | New page grids with backend metadata
ID-based Loader Tracker | Datasets | Dataset tabs + filters | 14 | Tabs plus per-tab filter wiring
ID-based Loader Tracker | Datasets | Query builder | 10 | Backend rule generation + UI builder states
ID-based Loader Tracker | Datasets | Per-tab data grids | 24 | Multiple grids with backend metadata
ID-based Loader Tracker | File Tracker | Mini sidebar for file scope | 4 | Compact navigation + context switching
ID-based Loader Tracker | File Tracker | Stepper and grid for file tracker | 10 | Stepper UX plus backend-fed grid
ID-based Loader Tracker | Load Tracker | Stepper cards for load progress | 10 | UI card build-out with state handling
ID-based Loader Tracker | Load Tracker | Data grid for ID-scoped loads | 20 | Backend column config + UI interactions
ID-based Loader Tracker | Mapping | Mapping data grid | 8 | UI grid + backend data contract
ID-based Loader Tracker | Mapping | Popup grid for mapping actions | 12 | Action popups, backend configuration, validations
ID-based Loader Tracker | Navigation | ID-specific tabs | 2 | Straightforward tab wiring
ID-based Loader Tracker | Related Files | Related files grid | 4 | Simple data grid fed by backend columns
ID-based Loader Tracker | Reports | Report filters | 16 | UI + backend filtering APIs
ID-based Loader Tracker | Reports | Score cards | 8 | UI charts tied to backend aggregations
ID-based Loader Tracker | Reports | Report data grids | 24 | UI data grids plus backend queries
ID-based Loader Tracker | Reports | Popup query builder & rules | 24 | Advanced query builder UX + backend rule handling
Load Tracker | Data Grid | Tracker grid with actions and polling | 16 | UI grid behavior, backend column config, expanded rows
Load Tracker | Filters | Filter coverage for all load tracker views | 6 | Backend-only query validation across filters

## Timeline
Phase | Focus
Month 1 | Foundational shell, dashboard experience, baseline load tracker
Month 2 | ID-based tracker core flows (tabs, mapping, file tracker)
Month 3 | Datasets, reporting, config hardening, global config rollout