# Clinical Migration Effort Estimate

Overall timeline: 480 hours (~60 days at 8 hrs/day, spanning about 3 months).

This plan highlights where UI work, backend query tuning, and shared configuration updates concentrate. Heavy hitters such as the ID-based Loader Tracker and Global Config require parallel UI/API delivery, while Login/Side Navigation are lighter refreshes.

| Module | Hours | Primary Focus | Where effort is concentrated |
| --- | --- | --- | --- |
| Login | 4 | Frontend UI refresh | Tighten login experience to align with new design system. |
| Side Navigation | 8 | Frontend UI refresh | Rebuild side navigation with interaction states and accessibility. |
| Dashboard | 38 | Mixed | Filters, data grids, and scorecards split across UI and API. |
| Load Tracker | 22 | Backend heavy | Filter tuning plus richer tracker grid interactions. |
| ID-based Loader Tracker | 226 | Large mixed workstream | End-to-end tracking experience including steppers, tabs, mapping, reports, and datasets. |
| Global Config | 182 | Data governance & rules | ICM/UCM grids plus data quality and source management. |

## Detailed workstreams

### Login

Tighten login experience to align with new design system.

Modernize login UI components (Frontend 4h; total 4h) — Whole UI effort

### Side Navigation

Rebuild side navigation with interaction states and accessibility.

Rebuild responsive side navigation (Frontend 8h; total 8h) — Whole UI effort

### Dashboard

Filters, data grids, and scorecards split across UI and API.

Module-level filter framework (Frontend 6h, Backend 6h; total 12h) — Factory setup + config-driven filters

Data grid definitions + RDS columns (Frontend 8h, Backend 8h; total 16h) — Column mapping + UI rendering

Score cards & queries (Frontend 5h, Backend 5h; total 10h) — Chart refresh + filter-aware queries

### Load Tracker

Filter tuning plus richer tracker grid interactions.

Audit and extend filters (Backend 6h; total 6h) — Pure backend query effort

Actionable data grid (polling, expanders) (Frontend 8h, Backend 8h; total 16h) — UI actions + backend column config

### ID-based Loader Tracker

End-to-end tracking experience including steppers, tabs, mapping, reports, and datasets.

Tab shell (Frontend 2h; total 2h) — Straightforward UI tabs

Stepper experience (Frontend 7h, Backend 3h; total 10h) — Card build-out for each step

Primary data grid (Frontend 10h, Backend 10h; total 20h) — Columns, actions, expansion views

Mini sidebar (Frontend 4h; total 4h) — Navigation UI

Stepper + grid (Frontend 6h, Backend 4h; total 10h) — Repeat flow for file-level view

Mapping data grid (Frontend 4h, Backend 4h; total 8h) — Shared UI/backend

Popup data grid actions (Frontend 6h, Backend 6h; total 12h) — Actions + backend config

Tabs and per-tab filters (Frontend 8h, Backend 6h; total 14h) — Filter wiring

Query builder (Frontend 5h, Backend 5h; total 10h) — Shared builder logic

Tab data grids (Frontend 12h, Backend 12h; total 24h) — Multiple dataset grids

Report filters (Frontend 8h, Backend 8h; total 16h) — UI + backend

Score cards (Frontend 4h, Backend 4h; total 8h) — Filter-aware KPIs

Report data grids (Frontend 12h, Backend 12h; total 24h) — UI + backend

Popup query builder & rules (Frontend 12h, Backend 12h; total 24h) — Dropdown logic + validations

Tabs + grids (Frontend 9h, Backend 9h; total 18h) — Columns + layout

Detail view grids (Frontend 9h, Backend 9h; total 18h) — Additional datagrid setup

Supporting data grid (Frontend 2h, Backend 2h; total 4h) — UI + backend columns

### Global Config

ICM/UCM grids plus data quality and source management.

ICM data grid (Frontend 12h; total 12h) — Grid shell

ICM grid actions (Frontend 8h; total 8h) — Action bar

ICM popups + nested grids (Frontend 10h, Backend 10h; total 20h) — Multiple popup datagrids

ICM rule checks (Frontend 6h, Backend 6h; total 12h) — Validation logic

UCM data grid (Frontend 12h; total 12h) — Grid shell

UCM grid actions (Frontend 8h; total 8h) — Action bar

UCM popups + nested grids (Frontend 10h, Backend 10h; total 20h) — Multiple popup datagrids

UCM rule checks (Frontend 6h, Backend 6h; total 12h) — Validation logic

Multi-step filters/forms (Frontend 21h, Backend 21h; total 42h) — Stepper + popup flow

Source data grid (Frontend 6h, Backend 6h; total 12h) — Grid shell

Source rules (Frontend 6h, Backend 6h; total 12h) — Rule definitions

Grid filters & column reset (Frontend 6h, Backend 6h; total 12h) — Filter interactions

## Key focus areas

Finalize configuration-driven filters early to avoid duplicate UI/backend changes.

Sequence ID-based tracker deliverables so datasets, reports, and config land in the same sprint.

Reserve backend capacity for Global Config data-quality rules and source governance.